## Sample_Project_Sample_CSV_Repor
Generated with www.fieldwire.com
Sample Project
2018-04-09 17:47
ID | Title | Priority | Category | Assignee | Start date | End date | Plan | X pos (%) | Y pos (%) | Location | Manpower | Cost | Plan folder | Plan Link | Created | Completed | Verified | Deleted | Last Updated | Tag 1 | Related task 1 | Related task 2 | Related task 3 | Checklist 1 | Checklist 2 | Checklist 3 | Checklist 4 | Checklist 5 | Checklist 6 | Checklist 7 | Checklist 8 | Checklist 9 | Checklist 10 | Checklist 11 | Checklist 12 | Checklist 13 | Checklist 14 | Checklist 15 | Message 1 | Message 2 | Message 3 | Message 4 | Message 5 | Message 6 | Message 7
1 | Review emergency egress plan with safety manager | 2 | Safety | bob@fieldwire.net | 2018-04-04 | 2018-04-04 | A2.01-1 | 0 | 0 |  |  |  | Architectural | Plan Link | 2018-04-04 01:24 |  |  |  | 2018-04-04 01:24 | [19 empty] | Bob Super: Review emergency egress plan with safety manager @A1.01 | Bob Super: Changed category to Safety
2 | Client approval on color palette | 1 | Design | katie@fieldwire.net | 2018-04-14 | 2018-04-14 | [8 empty] | 2018-04-04 01:24 |  |  |  | 2018-04-04 01:24 | client |  |  |  | Not set: paint (BSU) - 2018-04-04 | Not set: tile (BSU) - 2018-04-04 | Not set: cabinets (BSU) - 2018-04-04 | Not set: flooring (BSU) - 2018-04-04 | Not set: countertops (BSU) - 2018-04-04 | Not set: ceiling (ACT) (BSU) - 2018-04-04 | [9 empty] | Beth Engineer: Client approval on color palette | Beth Engineer: Changed category to Design | Beth Engineer: #client @KatieClient | Beth Engineer: Changed end date to 2018-04-14
3 | Found unmarked utility line in road | 1 | Demo | bob@fieldwire.net |  |  | C5.1 | 61.01 | 64.37 | Chestnut Street | 32 | 0 | Civil | Plan Link | 2018-04-04 01:24 | 2018-03-30 01:24 | 2018-03-30 01:24 |  | 2018-04-04 01:24 | change_order | Patching on Chestnut Street | [17 empty] | Bob Super: Found unmarked utility line in road | Bob Super: Appears to be abandoned. Need approval to remove. @P1 @Demo @KatieClient #change_order | Bob Super: Picture link | Katie Client: Please proceed with removing the pipe to maintain schedule. | Bob Super: Changed manpower to 32 man-hours | Bob Super: @Verified
4 | Sawcut along break in asphalt | 1 | Paving | james@fieldwire.net |  |  | C5.1 | 85.79 | 55.97 |  | 0 | 0 | Civil | Plan Link | 2018-04-04 01:24 |  |  |  | 2018-04-04 01:24 | [19 empty] | Bob Super: Sawcut along break in asphalt | Bob Super: Changed category to Paving | Bob Super: Picture link | Bob Super: Picture link | Bob Super: @P1 @JamesForeman
5 | Plumbing for faucet does not align with sink | 1 | Plumbing | bob@fieldwire.net |  |  | A2.01-1 | 55.73 | 39.49 |  | 24 |  | Architectural | Plan Link | 2018-04-04 01:24 |  |  |  | 2018-04-04 01:24 | rework | [18 empty] | Beth Engineer: Plumbing for faucet does not align with sink | Beth Engineer: Changed category to Plumbing | Beth Engineer: Changed owner to Bob Super | Beth Engineer: Changed priority to priority 1 | Beth Engineer: Picture link | Beth Engineer: #rework | Bob Super: Changed manpower to 24 man-hours
6 | Replace damaged carpet tile | 2 | Flooring | james@fieldwire.net | 2018-04-11 | 2018-04-11 | A2.01-1 | 56.1 | 58.64 | Room 203 | 8 | 250 | Architectural | Plan Link | 2018-04-04 01:24 |  |  |  | 2018-04-04 01:24 | rework |  |  |  | Yes: confirm moisture level is acceptable (JFO) - 2018-04-04 | Not set: apply adhesive (JFO) - 2018-04-04 | Not set: install carpet tile (JFO) - 2018-04-04 | Not set: install temp protection over carpet (JFO) - 2018-04-04 | [11 empty] | Beth Engineer: Replace damaged carpet tile | Beth Engineer: Picture link | Beth Engineer: @Flooring #rework | Beth Engineer: Changed manpower to 8 man-hours | Beth Engineer: Changed cost to 250 USD | Beth Engineer: I estimated the hours and cost. @JamesForeman, please confirm or edit.
7 | Room 106 wall completion | 3 | Drywall | beth@fieldwire.net |  |  | A2.01-1 | 60.36 | 64.24 | Room 106 |  |  | Architectural | Plan Link | 2018-04-04 01:24 |  |  |  | 2018-04-04 01:24 |  |  |  |  | Yes: Studs complete (BEN) - 2018-04-04 | Yes: Rough-in done (BEN) - 2018-04-04 | Yes: Rough inspection passed (BEN) - 2018-04-04 | Not set: Drywall installed (BEN) - 2018-04-04 | Not set: Tape and finish complete (BEN) - 2018-04-04 | Not set: Caulking complete (BEN) - 2018-04-04 | Not set: Ready for paint (BEN) - 2018-04-04 | Not set: Primed (BEN) - 2018-04-04 | Not set: Finish paint complete (BEN) - 2018-04-04
8 | Repair wall board once t-stat is moved | 2 | Drywall | james@fieldwire.net | [5 empty] | Room 104 |  |  |  |  | 2018-04-04 01:24 |  |  |  | 2018-04-04 01:24 |  | T-stat conflicts with shelving | [17 empty] | John Smith: Repair wall board once t-stat is moved @Drywall @JamesForeman
9 | Tape & finish gyp board | 2 | Drywall | john@fieldwire.net | [5 empty] | Room 104 |  |  |  |  | 2018-04-04 01:24 |  |  |  | 2018-04-04 01:24 |  | T-stat conflicts with shelving | [17 empty] | James Foreman: Tape & finish gyp board @Drywall @JohnSmith
10 | Repaint wall | 2 | Paint | john@fieldwire.net | [5 empty] | Room 104 |  |  |  |  | 2018-04-04 01:24 |  |  |  | 2018-04-04 01:24 |  | T-stat conflicts with shelving | [17 empty] | James Foreman: Repaint wall @Paint @JohnSmith
11 | Patching on Chestnut Street | 2 | Paving | bob@fieldwire.net | 2018-04-10 | 2018-04-12 | C5.1 | 58.59 | 64.55 |  |  |  | Civil | Plan Link | 2018-04-04 01:24 |  |  |  | 2018-04-04 01:24 |  | Found unmarked utility line in road | [17 empty] | Bob Super: Patching on Chestnut Street @Paving | Bob Super: Changed start date to 2018-04-10 | Bob Super: Changed end date to 2018-04-12
12 | T-bar installation | 2 | Ceilings | james@fieldwire.net | 2018-04-03 | 2018-04-08 | A2.03-1 | 55.57 | 66.73 | Lobby |  |  | Architectural | Plan Link | 2018-04-04 01:24 |  |  |  | 2018-04-04 01:24 |  | A-type fixture installation | [17 empty] | Bob Super: T-bar installation @Ceilings @JamesForeman | James Foreman: In progress | James Foreman: Changed start date to 2018-04-03 | James Foreman: Changed end date to 2018-04-08 | James Foreman: Picture link
13 | A-type fixture installation | 2 | Electrical | john@fieldwire.net |  |  | E.3 | 43.05 | 35.34 | Chestnut Street |  |  | Electrical | Plan Link | 2018-04-04 01:24 |  |  |  | 2018-04-04 01:24 |  | T-bar installation | [17 empty] | Bob Super: A-type fixture installation @Electrical @JohnSmith | John Smith: Waiting on t-bar installation. Plan to start work on Monday. | John Smith: Picture link
14 | Sawcutting sidewalk in progress | 3 | Demo | bob@fieldwire.net |  |  | C4.1 | 36.7 | 68.59 |  |  |  | Civil | Plan Link | 2018-04-04 01:24 |  |  |  | 2018-04-04 01:24 | [19 empty] | Bob Super: Sawcutting sidewalk in progress @Demo | Bob Super: Picture link | Bob Super: Picture link | Bob Super: Picture link | Bob Super: Changed priority to priority 3
15 | Install conduit for EF-4 fan | 1 | Electrical | john@fieldwire.net |  |  | E.4 | 41.29 | 49.51 |  |  |  | Electrical | Plan Link | 2018-04-04 01:24 |  |  |  | 2018-04-04 01:24 |  | EF-4 fan installation | [17 empty] | Beth Engineer: Install conduit for EF-4 fan @Electrical @JohnSmith @P1 | Beth Engineer: Picture link
16 | EF-4 fan installation | 2 | HVAC | james@fieldwire.net | [10 empty] | 2018-04-04 01:24 |  |  |  | 2018-04-04 01:24 |  | Install conduit for EF-4 fan | [17 empty] | Beth Engineer: EF-4 fan installation @HVAC @JamesForeman
17 | Slab-on-grade pour | 2 | Concrete | bob@fieldwire.net |  |  | S2.01a | 23.3 | 71.58 |  |  |  | Structural | Plan Link | 2018-04-04 01:24 |  |  |  | 2018-04-04 01:24 |  |  |  |  | Yes: excavation is in correct location (BSU) - 2018-04-04 | Yes: base is installed per design (BSU) - 2018-04-04 | No: base compacted and approved (BSU) - 2018-04-04 | Not set: rebar is installed per design (BSU) - 2018-04-04 | Not set: rebar spacers/chairs installed as needed (BSU) - 2018-04-04 | Not set: rebar is approved by inspector (BSU) - 2018-04-04 | Not set: formwork is vertical (BSU) - 2018-04-04 | Not set: adequate bracing is installed (BSU) - 2018-04-04 | Not set: form oil is applied (BSU) - 2018-04-04 | Not set: concrete is ordered (BSU) - 2018-04-04 | Not set: concrete testing has been organized (BSU) - 2018-04-04 | Not set: any necessary permitting has been obtained (BSU) - 2018-04-04 | Not set: curing materials are onsite (BSU) - 2018-04-04 |  |  | Bob Super: Slab-on-grade pour @Concrete | Bob Super: Waiting on geotechnical engineer visit tomorrow for compaction approval.
18 | Safety Walk | 1 | Safety | james@fieldwire.net | 2018-04-03 | 2018-04-03 | [8 empty] | 2018-04-04 01:24 | 2018-04-03 01:24 |  |  | 2018-04-04 01:24 |  |  |  |  | Yes: Is site secure from public? (JSM) - 2018-04-04 | Yes: Are paths of travel clear? (JSM) - 2018-04-04 | Yes: Are shade and potable drinking water available? (JSM) - 2018-04-04 | Yes: Are toilets clean and well stocked? (JSM) - 2018-04-04 | Yes: Are fire extinguishers available and up to date? (JSM) - 2018-04-04 | Yes: Are all people onsite wearing appropriate PPE? (JSM) - 2018-04-04 | Yes: Is appropriate lighting provided? (JSM) - 2018-04-04 | Yes: Are fall protection systems in place for anyone who could fall over 6 feet? (JSM) - 2018-04-04 | Yes: Are ladders being used appropriately? (JSM) - 2018-04-04 | Yes: Are electrical cords in good order? (JSM) - 2018-04-04 | Yes: Are all holes greater than 2" in diameter covered and/or marked? (JSM) - 2018-04-04 | Yes: Are all impalement hazards capped/covered? (JSM) - 2018-04-04 | Yes: Is any scaffolding in proper working order? (JSM) - 2018-04-04 | N/A: Do any trenches over 5 feet deep have proper cave-in protection? (JSM) - 2018-04-04 | N/A: Do all confined spaces have proper emergency equipment and require appropriate PPE? (JSM) - 2018-04-04 | John Smith: Safety Walk | John Smith: Changed category to Safety | John Smith: Completed task | John Smith: Picture link | John Smith: Picture link | John Smith: Picture link | John Smith: Changed start date to 2018-04-03
19 | Clean up needed | 2 | Clean Up | james@fieldwire.net |  |  | A2.01-1 | 46.72 | 74.19 |  |  |  | Architectural | Plan Link | 2018-04-04 01:24 |  |  |  | 2018-04-04 01:24 | [19 empty] | Bob Super: Clean up needed @CleanUp @JamesForeman | Bob Super: Picture link
20 | T-stat conflicts with shelving | 2 | HVAC | john@fieldwire.net |  |  | A2.01-1 | 63.62 | 72.95 | Room 104 |  |  | Architectural | Plan Link | 2018-04-04 01:24 |  |  |  | 2018-04-04 01:24 | punch | Repair wall board once t-stat is moved | Repaint wall | Tape & finish gyp board | [15 empty] | Katie Client: T-stat conflicts with shelving @HVAC @JohnSmith #punch | Katie Client: Picture link